## Backlog
# | Task | Priority (1-5) | % Complete | Depends on: | Creation Date | Completion Date | Est. Total Hours Required | Est. Hours Remaining | # of hours taken | Comments
6 | Fix all memory leaks | 4 | 100% |  | 2012-02-15 | 2012-02-15 | 4 | 0 | 4.5
10 | Create Sequence Diagram for spell-casting behavior | 4 | 100% |  | 2012-02-15 | 2012-02-15 | 0.5 | 0 | 1
11 | Create basic Sequence Diagram for sample Messenger behavior | 4 | 100% |  | 2012-02-15 | 2012-02-16 | 0.5 | 0 | 0.5
20 | Find out WHAT THE FUCK is causing Camera.h/.cpp to arbitrarily break builds | 4 | 100% |  | 2012-02-15 | 2012-02-15 | 6 | 0 | 0
26 | const-correct all code (accessors, etc) | 4 | 100% |  | 2012-02-15 | 2012-02-15 | 1 | 0 | 0
40 | Figure out what was causing strange issues with EntityView::setEntity() not using pass-by-reference | 4 | 100% |  | 2012-02-19 | 2012-02-19 | 2 | 0 | 0
41 | Fix errors that are occurring when running Release mode & Fix memory leaks | 4 | 100% |  | 2012-02-19 | 2012-02-20 | 2 | 0
52 | Add unit tests and acceptance tests for ALL THE THINGS | 4 | 0% |  | 2012-07-24 |  | 40 | 40
2 | Fix camera to not deal with projection matrix | 3 | 100% |  | 2012-02-15 | 2012-02-15 | 1 | 0 | 0.66667
3 | Shift responsibility of generating vertices to LandscapeGenerator instead of LandscapeView | 3 | 100% |  | 2012-02-15 | 2012-02-15 | 1 | 0 | 1
4 | Fix ownership/aggregation of all landscape objects between GameState and ViewManager | 3 | 100% |  | 2012-02-15 | 2012-02-16 | 1 | 0 | 0.5
5 | Create Server project & Client project | 3 | 100% |  | 2012-02-15 | --- | 2 | 0 | 2.5
12 | Create Backlog | 3 | 100% |  | 2012-02-15 | 2012-02-15 | 0.5 | 0.5 | 0.5
15 | Learn sufficiently enough of the WinSock API | 3 | 100% |  | 2012-02-15 | --- | 20 | 0 | 2
16 | Create test IO Control Port demonstration | 3 | 100% | 15 | 2012-02-15 | --- | 15 | 0 | 7
18 | Implement multi-threading control structures | 3 | 100% |  | 2012-02-15 | 2012-02-19 | 10 | 0 | 1
19 | Create a robust error/return code system, implement across the board | 3 | 100% |  | 2012-02-15 | 2012-02-19 | 4 | 0 | 3
24 | Make the BattleViewManager into a singleton class | 3 | 100% |  | 2012-02-15 | 2012-02-15 | 1 | 0
34 | Create Entities and the EntityManager (try for simple movable entity with 'IJKL' controls) | 3 | 100% |  | 2012-02-18 | 2012-02-20 | 10 | 10 | 2
38 | Create/Implement Model3D class which encapsulates Ibuffer, Vbuffer, Vertex type, stride, offset, etc | 3 | 0% |  | 2012-02-19 |  | 1 | 1
43 | Figure out why the hell the camera is changing position when we move our PudEntity -___- | 3 | 100% |  | 2012-02-20 | 2012-02-21 | 2 | 2
44 | Create a public 'request' interface and private 'model-modifying' interface for EntityManager | 3 | 100% |  | 2012-02-21 | 2012-02-21 | 1 | 3
45 | Implement outgoing net handling for Server, Incoming handling for Client | 3 | 0% |  | 2012-03-27 |  | 15 | 15 |  | X
46 | Implement Message Manager | 3 | 100% |  | 2012-03-27 |  | 6 | 0
47 | Create shared interface/abstract class for EMRequestHandler and EMMessageHandler | 3 | 100% |  | 2012-03-27 |  | 1 | 0
48 | Implement Error Logging Mechanism | 3 | 0% |  | 2012-03-27 |  | 5 | 5
50 | Implement Server to send Landscape structure to client | 3 | 0% | 45 | 2012-07-24 |  | 6 | 6
51 | Implement Client to request creation of entities from server, server to tell client to create entities | 3 | 0% | 45, ??? | 2012-07-24 |  | 10 | 10
53 | Make new video presentation of project | 3 | 0% |  | 2012-08-04 |  |  | 0
54 | Move Project to GitHub instead of local | 3 | 0% |  | 2014-08-04 |  | 1 | 1
1 | Add Input Manager/Create More refined Input Handling | 2 | 0% |  | 2012-02-15 |  | 10 | 10
17 | Comb through all TODO's, create corresponding backlog entries | 2 | 0% |  | 2012-02-15 |  | 0.5 | 0.5
21 | Set up doxygen to build off of project | 2 | 0% |  | 2012-02-15 |  | 1 | 1
22 | Write doxygen comments for alllll them functions | 2 | 0% |  | 2012-02-15 |  | 2 | 2
23 | Investigate and resolve error: [ STATE_SETTING WARNING #55: SETPRIVATEDATA_CHANGINGPARAMS ] | 2 | 100% |  | 2012-02-15 | 2012-02-15 | 2 | 0
27 | Create HUD skeleton, move frame statistics to it | 2 | 0% |  | 2012-02-15 |  | 1 | 1
28 | Decide if we need a ControllerManager, where LandscapeController should be created/destroyed | 2 | 100% |  | 2012-02-16 | 2012-02-16 | 0.5 | 0 | 0.5
29 | Shift responsibility of destroying landscape to landscape itself, rather than LandscapeGenerator | 2 | 0% |  | 2012-02-16 |  | 0.5 | 0.5
30 | Look into backup/svn solution/github | 2 | 0% |  | 2012-02-16 |  | 1 | 1
32 | Introduce lighting, light the LandscapeView (review + coding + debugging) | 2 | 0% |  | 2012-02-18 |  | 5 | 5
33 | Introduce texturing, texture the LandscapeView (learning + get textures + coding + debugging) | 2 | 0% |  | 2012-02-18 |  | 10 | 10
35 | Implement RC_ERR macro which will trace the given ReturnCode error at the line/file it occurred. | 2 | 0% | 48 | 2012-02-19 |  | 1 | 1
36 | Modify grid/landscape/entitymanager to account for multiple entities on a single gridunit | 2 | 0% |  | 2012-02-19 |  | 1 | 1
42 | Figure out why some drawn objects are lagging behind at lower frame rates (eg, 500x500 grid) | 2 | 100% |  | 2012-02-20 | 2012-02-21 | 1 | 0
9 | Reorganize file system heirarchy | 1 | 100% |  | 2012-02-15 | 2012-02-19 | 0.5 | 0 | 0.5
13 | Spruce up backlog, visually. Add scaling colors for important benchmarks/indicators. | 1 | 100% |  | 2012-02-15 | 2012-02-15 | 0.5 | 0 | 0
14 | Create Timesheet | 1 | 100% |  | 2012-02-15 | 2012-02-15 | 0.5 | 0 | 0.5
25 | Redesign Landscape to allow multipe GridUnits per column | 2 | 0% |  | 2012-02-15 |  | 5 | 5
31 | Move docs over to new project folder | 1 | 100% |  | 2012-02-18 | 2012-02-19 | 0 | 0
39 | Improve camera to use more intuitive controls | 1 | 0% |  | 2012-02-19 |  | 1 | 1
49 | Set up JIRA or Bugzilla tracking for project | 1 | 0% |  | 2012-07-24 |  | 2 | 2
7 | Create MockMessenger, Messenger, Messages (MockMessages?) |  |  |  | 2012-02-15 |  | 20 | 20 | 3 | X
8 | Integrate Mock Messenger dependency into manager systems |  |  | 7 | 2012-02-15 |  | 15 | 15 |  | X
37 | Take care of tax stuff!!!!! See skype conversation!!!!!! |  |  |  | 2012-02-19 |  |  | 0
55 | Eliminate redundancy (improve efficiency) of parcel & parcel buffer mechanics | 2 | 0% |  |  |  |  | 0
56 | [7 empty] | 0
57 | [7 empty] | 0
58 | [7 empty] | 0
59 | [7 empty] | 0
60 | [7 empty] | 0
61 | [7 empty] | 0
|  |  | 0% |  |  |  | 250.5 | 169.5 | 30.6667
<100%
Note on C1: Andrew: 1-Trivial 2-Minor 3-Major 4-Critical 5-Blocker
Note on K3: Andrew: Needs further consideration. Pretty much done for the time being though. 2/15/2012
Note on K4: Andrew: Really only a basic diagram, still more depth is needed, too foggy to make right now. Should consider bookmarked StackOverflow link on MMO IOCP usage when looking into this further, there was a very well constructed comment on the issue.
Note on K7: Andrew: What the fuck? All the sudden this works without a problem. Something must have indirectly been causing the problem, though it looked like it was pretty obviously failing because I was passing an Entity* by value and not by reference (granted, logically, either should work I believe). I haven't changed any code that I would think would have any effect on how this code was working since I recorded the issue. Perhaps there were some lingering ghosts in the EntityView code that got shoo'd away when I added a new test function to the EntityView.h file and recompiled. I don't know...
Note on K13: Andrew: Required changes to LandscapeGenerator due to conflict with LandscapeView & BattleViewManager #includes. Had to move LandscapeView generation code over to a static function of the LandscapeView class (instead of making a LandscapeViewGenerator). Not really happy with this design choice, but I don't see any better alternative at the moment.
Note on K22: Andrew: Note to self: Always apply the pass AFTER setting constant buffer values.
Note on K23: Andrew: Initially wanted to create derived ClientEntityManager and ServerEntityManager classes, but due to technical details (mostly revolving around EntityManager being a singleton class), I decided for a different implementation, in which the EntityManager contains a reference to an (abstract) EMRequestHandler, the concrete subclasses for which define our separate client/server 'request' interfaces. Unfortunately, this has resulted in a less-than-savory Preprocessor macro dependency in EntityManager.h, but overall I think the design should be suitable.
Note on K36: Andrew: Can't fix, issue with draw text. Won't be an issue if we migrate to DX11 (which will require some code changes)
Note on K45: Andrew: Note to self: Always apply the pass AFTER setting constant buffer values.